## WBS chi tiết
Mã | Cấp | Tên | Sprint | Role | SWP | Giờ | Độ tin | Trạng thái (S1 giả lập) | GitHub
EP-00 | Epic | Nền tảng: Azure, CI/CD, khung app, xác thực và cơ chế dùng chung |  |  | 292 | 541.5 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/1
EP00-I01 | Issue | Viết ADR kiến trúc đích Azure thay ADR-002 và ADR-012 | S0 | SA | 13 | 24 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/2
EP00-I01-S01 | Sub-issue | Soạn ADR logic nghiệp vụ trên App Service, DB giữ ràng buộc | S0 | SA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/3
EP00-I01-S02 | Sub-issue | Soạn ADR hạ tầng Azure, môi trường và DR | S0 | SA | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/4
EP00-I01-S03 | Sub-issue | Cập nhật ARCH_system-overview theo ADR mới | S0 | SA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/5
EP00-I01-S04 | Sub-issue | Review chéo ADR và xin APV | S0 | PM | 1 | 2 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/6
EP00-I02 | Issue | Dựng IaC môi trường dev và test trên Azure | S0 | Infra | 16 | 29.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/7
EP00-I02-S01 | Sub-issue | Viết IaC mạng và App Gateway WAF | S0 | Infra | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/8
EP00-I02-S02 | Sub-issue | Viết IaC App Service, PostgreSQL Flexible, Key Vault | S0 | Infra | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/9
EP00-I02-S03 | Sub-issue | Viết IaC Blob, Service Bus, Functions, App Insights | S0 | Infra | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/10
EP00-I02-S04 | Sub-issue | Review IaC dev / test | S0 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/11
EP00-I03 | Issue | Dựng pipeline CI/CD cho repo code | S0 | Infra | 13 | 24 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/12
EP00-I03-S01 | Sub-issue | Dựng CI build, test, lint, quét license / secret | S0 | Infra | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/13
EP00-I03-S02 | Sub-issue | Dựng CD dev / test và bước migration DB | S0 | Infra | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/14
EP00-I03-S03 | Sub-issue | Chạy test DB trên PostgreSQL trong CI | S0 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/15
EP00-I04 | Issue | Dựng môi trường UAT và cổng duyệt release | S5 | Infra | 7 | 13 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/16
EP00-I04-S01 | Sub-issue | Viết IaC môi trường UAT | S5 | Infra | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/17
EP00-I04-S02 | Sub-issue | Thêm cổng duyệt release và smoke test | S5 | Infra | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/18
EP00-I05 | Issue | Dựng môi trường prod và DR Japan West | S6 | Infra | 14 | 26 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/19
EP00-I05-S01 | Sub-issue | Viết IaC prod | S6 | Infra | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/20
EP00-I05-S02 | Sub-issue | Cấu hình replica PostgreSQL và sao chép Blob sang Japan West | S6 | Infra | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/21
EP00-I05-S03 | Sub-issue | Review quyền truy cập prod | S6 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/22
EP00-I06 | Issue | Che dữ liệu khi chép sang môi trường dưới | S5 | Infra | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/23
EP00-I07 | Issue | Dựng khung modular monolith theo 9 module | S0 | BE | 13 | 24 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/24
EP00-I07-S01 | Sub-issue | Viết DD khung module và quy ước API | S0 | SA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/25
EP00-I07-S02 | Sub-issue | Scaffold 9 module, lớp API và correlation ID | S0 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/26
EP00-I07-S03 | Sub-issue | Thêm luật kiểm kiến trúc vào CI | S0 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/27
EP00-I08 | Issue | Định nghĩa cổng adapter Auth, Storage, Mail, Map, Queue | S1 | BE | 7 | 13 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/28
EP00-I08-S01 | Sub-issue | Viết 5 interface và adapter giả | S1 | BE | 4 | 7.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/29
EP00-I08-S02 | Sub-issue | Thêm luật CI cấm gọi SDK hạ tầng ngoài adapter | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/30
EP00-I09 | Issue | Dựng nền schema DB và quy ước dữ liệu | S1 | BE | 11 | 20.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/31
EP00-I09-S01 | Sub-issue | Chọn công cụ migration và tạo schema wms | S0 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/32
EP00-I09-S02 | Sub-issue | Viết mẫu event bất biến + version + view hiện hành | S1 | BE | 5 | 9.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/33
EP00-I09-S03 | Sub-issue | Kiểm CI kiểu cột thời điểm và mã nghiệp vụ | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/34
EP00-I10 | Issue | Chuyển bảng mã sang giá trị ASCII và tách nhãn JA | S5 | BE | 13 | 24 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/35
EP00-I10-S01 | Sub-issue | Sinh CHECK và bảng tra nhãn từ code-definitions | S5 | BE | 4 | 7.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/36
EP00-I10-S02 | Sub-issue | Viết thành phần hiển thị nhãn cho UI / CSV | S5 | FE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/37
EP00-I10-S03 | Sub-issue | Viết hàm kiểm chuyển trạng thái theo §5 | S5 | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/38
EP00-I10-S04 | Sub-issue | Test không chữ Nhật trong DB | S5 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/39
EP00-I11 | Issue | Đăng nhập Entra ID có chọn 職務 trước và kiểm 職務 được gán | S1 | BE | 16 | 29.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/40
EP00-I11-S01 | Sub-issue | Viết DD COM-01 và luồng đăng nhập | S0 | SA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/41
EP00-I11-S02 | Sub-issue | BE kiểm 職務 được gán và ghi audit đăng nhập | S1 | BE | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/42
EP00-I11-S03 | Sub-issue | FE màn COM-01 | S1 | FE | 4 | 7.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/43
EP00-I11-S04 | Sub-issue | Ca kiểm thử đăng nhập theo 8 職務 | S1 | QA | 5 | 9.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/44
EP00-I12 | Issue | Lưu phiên một 職務 phía server | S1 | BE | 9 | 16.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/45
EP00-I12-S01 | Sub-issue | Viết DD lưu phiên một 職務 | S0 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/46
EP00-I12-S02 | Sub-issue | BE session store và middleware 職務 | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/47
EP00-I12-S03 | Sub-issue | Ca kiểm thử phiên và đổi 職務 | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/48
EP00-I13 | Issue | Bắt MFA theo 職務 được gán | S1 | BE | 9 | 16.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/49
EP00-I13-S01 | Sub-issue | BE kiểm amr theo vai được gán | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/50
EP00-I13-S02 | Sub-issue | Cấu hình Conditional Access cho vai đặc quyền | S1 | Infra | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/51
EP00-I13-S03 | Sub-issue | Ca kiểm thử né MFA | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/52
EP00-I14 | Issue | Kiểm quyền theo 職務 ở lớp API theo ma trận | S1 | BE | 14 | 26 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/53
EP00-I14-S01 | Sub-issue | Bảng role_permission và nạp qua release | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/54
EP00-I14-S02 | Sub-issue | Middleware quyền và luật CI khai báo quyền | S1 | BE | 5 | 9.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/55
EP00-I14-S03 | Sub-issue | Test ma trận 8 職務 | S1 | QA | 6 | 11 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/56
EP00-I15 | Issue | Dựng cơ chế duyệt hai người dùng chung | S1 | BE | 6 | 11 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/57
EP00-I15-S01 | Sub-issue | Thư viện kiểm người duyệt | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/58
EP00-I15-S02 | Sub-issue | Ca kiểm thử tự duyệt và người sửa giữa chừng | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/59
EP00-I16 | Issue | Cài thứ tự khóa chung theo ADR-003 | S1 | BE | 14 | 26 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/60
EP00-I16-S01 | Sub-issue | Viết DD bảng khóa chung cho mọi luồng ghi tồn | S0 | SA | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/61
EP00-I16-S02 | Sub-issue | Helper khóa trong transaction | S1 | BE | 4 | 7.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/62
EP00-I16-S03 | Sub-issue | Test đồng thời và deadlock | S1 | QA | 4 | 7.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/63
EP00-I17 | Issue | Dựng sổ idempotency dùng chung cho thao tác ghi | S1 | BE | 16 | 29.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/64
EP00-I17-S01 | Sub-issue | Viết DD hợp đồng idempotency | S0 | SA | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/65
EP00-I17-S02 | Sub-issue | Middleware và bảng biên nhận | S1 | BE | 6 | 11 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/66
EP00-I17-S03 | Sub-issue | Ca kiểm thử gửi lặp | S1 | QA | 4 | 7.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/67
EP00-I18 | Issue | Dựng khung bảng quy tắc có version | S1 | BE | 9 | 16.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/68
EP00-I18-S01 | Sub-issue | DB và ràng buộc hiệu lực | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/69
EP00-I18-S02 | Sub-issue | Hàm chọn version hiệu lực | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/70
EP00-I18-S03 | Sub-issue | Ca kiểm thử biên hiệu lực | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/71
EP00-I19 | Issue | Dựng temperature_policy_version và đánh giá nhiệt theo version | S1 | BE | 9 | 16.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/72
EP00-I19-S01 | Sub-issue | DB và dữ liệu khởi tạo ngưỡng | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/73
EP00-I19-S02 | Sub-issue | API đánh giá nhiệt theo version | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/74
EP00-I19-S03 | Sub-issue | Ca kiểm thử biên 3 dải | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/75
EP00-I20 | Issue | Dựng duty_rule_version nạp qua release | S1 | BE | 9 | 16.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/76
EP00-I20-S01 | Sub-issue | DB và script nạp ルール版 | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/77
EP00-I20-S02 | Sub-issue | Bước release nạp ルール版 | S1 | Infra | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/78
EP00-I20-S03 | Sub-issue | Ca kiểm thử nạp sai người duyệt | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/79
EP00-I21 | Issue | Version hóa quy tắc 1/3・1/2 theo 顧客×SKU | S1 | BE | 7 | 13 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/80
EP00-I21-S01 | Sub-issue | DB và API tra rule hợp đồng | S1 | BE | 4 | 7.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/81
EP00-I21-S02 | Sub-issue | Ca kiểm thử rule trống và không hợp đồng | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/82
EP00-I22 | Issue | Dựng tham số cấu hình có version (config_parameter) | S1 | BE | 7 | 13 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/83
EP00-I22-S01 | Sub-issue | DB và API đọc tham số hiệu lực | S1 | BE | 4 | 7.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/84
EP00-I22-S02 | Sub-issue | Bước release nạp tham số | S1 | Infra | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/85
EP00-I23 | Issue | Dựng catalog mã thông điệp từ error-codes 1.6.0 | S1 | BE | 7 | 13 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/86
EP00-I23-S01 | Sub-issue | Bộ sinh catalog và kiểm CI | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/87
EP00-I23-S02 | Sub-issue | Thành phần hiển thị thông điệp | S1 | FE | 1 | 2 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/88
EP00-I23-S03 | Sub-issue | Đối chiếu mã theo từng spec | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/89
EP00-I24 | Issue | Dựng audit_log chỉ thêm | S1 | BE | 11 | 20.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/90
EP00-I24-S01 | Sub-issue | DB, trigger và quyền chỉ INSERT | S1 | BE | 5 | 9.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/91
EP00-I24-S02 | Sub-issue | Thư viện ghi audit trong transaction | S1 | BE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/92
EP00-I24-S03 | Sub-issue | Ca kiểm thử chỉ thêm và rollback | S1 | QA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/93
EP00-I25 | Issue | Dựng thư viện gói xuất có manifest SHA-256 | S2 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/94
EP00-I25-S01 | Sub-issue | Chuẩn hóa CSV, hash và manifest | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/95
EP00-I25-S02 | Sub-issue | Ca kiểm thử tái tạo hash | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/96
EP00-I26 | Issue | Phân vùng tháng cho bảng lớn | S1 | BE | 11 | 20.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/97
EP00-I26-S01 | Sub-issue | Viết DD khóa và unique trên bảng partition | S0 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/98
EP00-I26-S02 | Sub-issue | DDL partition và job tạo partition | S1 | BE | 5 | 9.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/99
EP00-I26-S03 | Sub-issue | Test partition pruning | S1 | QA | 3 | 5.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/100
EP00-I27 | Issue | Dựng khung chạy batch trên Functions | S1 | BE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/101
EP00-I27-S01 | Sub-issue | Khung trigger và khóa lần chạy | S1 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/102
EP00-I27-S02 | Sub-issue | Hạ tầng Functions và lịch JST | S1 | Infra | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/103
EP00-I27-S03 | Sub-issue | Ca kiểm thử chạy chồng và lỗi | S1 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/104
EP00-I28 | Issue | Lưu tệp đính kèm trên Blob và container WORM | S2 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/105
EP00-I28-S01 | Sub-issue | Chính sách WORM và container | S2 | Infra | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/106
EP00-I28-S02 | Sub-issue | API tải lên / tải về qua StoragePort | S2 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/107
EP-10 | Epic | NFR, セキュリティ và 可観測性 |  |  | 193 | 358 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/108
EP10-I01 | Issue | Dựng màn COM-04 lỗi chung | S1 | FE | 9 | 16.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/109
EP10-I01-S01 | Sub-issue | Viết DD COM-04 | S0 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/110
EP10-I01-S02 | Sub-issue | FE màn COM-04 | S1 | FE | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/111
EP10-I01-S03 | Sub-issue | Ca kiểm thử COM-04 | S1 | QA | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/112
EP10-I02 | Issue | Dựng màn COM-02 menu theo 職務 | S5 | FE | 15 | 28 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/113
EP10-I02-S01 | Sub-issue | Viết DD COM-02 | S5 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/114
EP10-I02-S02 | Sub-issue | API đếm việc cần làm theo 職務 | S5 | BE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/115
EP10-I02-S03 | Sub-issue | FE màn COM-02 (PC và ハンディ) | S5 | FE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/116
EP10-I02-S04 | Sub-issue | Ca kiểm thử menu 8 職務 | S5 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/117
EP10-I03 | Issue | Dựng COM-03 khóa phiên theo lớp thiết bị | S5 | FE | 15 | 28 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/118
EP10-I03-S01 | Sub-issue | Viết DD COM-03 | S5 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/119
EP10-I03-S02 | Sub-issue | BE hết phiên và audit khóa | S5 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/120
EP10-I03-S03 | Sub-issue | FE COM-03 cảnh báo và khóa | S5 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/121
EP10-I03-S04 | Sub-issue | Ca kiểm thử khóa phiên | S5 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/122
EP10-I04 | Issue | Xác định lớp thiết bị ở server và chỉ cho duyệt trên PC | HARD | BE | 12 | 22 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/123
EP10-I04-S01 | Sub-issue | BE đọc claim thiết bị và chặn duyệt | HARD | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/124
EP10-I04-S02 | Sub-issue | Bộ lọc thiết bị trong Conditional Access | HARD | Infra | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/125
EP10-I04-S03 | Sub-issue | Ca kiểm thử duyệt theo thiết bị | HARD | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/126
EP10-I05 | Issue | Mã hóa dữ liệu khi truyền, khi lưu và trong tệp | HARD | Infra | 12 | 22 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/127
EP10-I05-S01 | Sub-issue | Cấu hình TLS và mã hóa lưu DB / Blob | HARD | Infra | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/128
EP10-I05-S02 | Sub-issue | Mã hóa cột cá nhân ở ứng dụng | HARD | BE | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/129
EP10-I05-S03 | Sub-issue | Kiểm mã hóa | HARD | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/130
EP10-I06 | Issue | Quản lý bí mật bằng Key Vault và managed identity | S0 | Infra | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/131
EP10-I07 | Issue | Dựng quan sát: log có cấu trúc, trace, metric, alert | S2 | Infra | 12 | 22 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/132
EP10-I07-S01 | Sub-issue | Chốt quy ước log có cấu trúc | S1 | SA | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/133
EP10-I07-S02 | Sub-issue | Gắn log / trace cho API và batch | S2 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/134
EP10-I07-S03 | Sub-issue | Alert P0 và dashboard | S2 | Infra | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/135
EP10-I08 | Issue | Cảnh báo batch không chạy hoặc chạy quá giờ | ST | Infra | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/136
EP10-I09 | Issue | Soạn runbook sự cố P0 | S6 | Infra | 7 | 13 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/137
EP10-I09-S01 | Sub-issue | Viết runbook theo từng alert P0 | S6 | Infra | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/138
EP10-I09-S02 | Sub-issue | Diễn tập runbook trên test | S6 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/139
EP10-I10 | Issue | Dựng bộ dữ liệu giả cỡ thật để đo hiệu năng | S4 | QA | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/140
EP10-I11 | Issue | Đo truy vết 3 năm ≤ 60 giây và quyết A-3 | S5 | BE | 9 | 16.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/141
EP10-I11-S01 | Sub-issue | Tối ưu chỉ mục truy vết | S5 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/142
EP10-I11-S02 | Sub-issue | Đo và báo cáo PERF-02 | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/143
EP10-I12 | Issue | Load test p95 đọc ≤ 2 giây, ghi ≤ 3 giây với 80 phiên | HARD | QA | 13 | 24 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/144
EP10-I12-S01 | Sub-issue | Viết kịch bản load test theo vai | S6 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/145
EP10-I12-S02 | Sub-issue | Chạy load test và báo cáo | HARD | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/146
EP10-I12-S03 | Sub-issue | Tối ưu điểm nghẽn | HARD | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/147
EP10-I13 | Issue | Cấu hình backup và PITR cho PostgreSQL và Blob | S6 | Infra | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/148
EP10-I14 | Issue | Diễn tập restore và chuyển vùng DR, đo RTO 4 giờ | HARD | Infra | 12 | 22 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/149
EP10-I14-S01 | Sub-issue | Viết DD luồng restore và chuyển vùng | S6 | Infra | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/150
EP10-I14-S02 | Sub-issue | Chạy diễn tập và đo | HARD | Infra | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/151
EP10-I14-S03 | Sub-issue | Kiểm dữ liệu sau restore | HARD | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/152
EP10-I15 | Issue | Cấu hình HA đạt 99,5% trong giờ phục vụ | S6 | Infra | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/153
EP10-I16 | Issue | Kiểm hành vi mất mạng ở màn kho và màn PC | ST | QA | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/154
EP10-I17 | Issue | Dựng hiển thị JST và định dạng Nhật dùng chung | S5 | FE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/155
EP10-I18 | Issue | Đưa kiểm WCAG 2.2 AA tự động vào CI | S5 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/156
EP10-I22 | Issue | Kiểm tay WCAG 2.2 AA toàn bộ màn | HARD | QA | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/157
EP10-I19 | Issue | Kiểm ma trận quyền toàn hệ thống | HARD | QA | 12 | 22 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/158
EP10-I20 | Issue | Lập gói bằng chứng bảo mật: threat model, SBOM, quét lỗ hổng | HARD | SA | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/159
EP10-I21 | Issue | Tổng hợp bằng chứng NFR cho nghiệm thu | ST | PM | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/160
EP-08 | Epic | マスタ: vòng đời master, 契約, 温度ポリシー, lưu giữ và purge |  |  | 193 | 358 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/161
EP08-I01 | Issue | Dựng khung vòng đời master dùng chung | S1 | BE | 11 | 20.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/162
EP08-I01-S01 | Sub-issue | Viết DD SCR-14 phần chung và vòng đời master | S0 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/163
EP08-I01-S02 | Sub-issue | API vòng đời master | S1 | BE | 5 | 9.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/164
EP08-I01-S03 | Sub-issue | Ca kiểm thử vòng đời | S1 | QA | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/165
EP08-I02 | Issue | Dựng 14-01 SKUマスタ | S1 | FE | 13 | 24 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/166
EP08-I02-S01 | Sub-issue | Viết DD SCR-14 vùng 14-01 | S0 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/167
EP08-I02-S02 | Sub-issue | API SKU | S1 | BE | 4 | 7.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/168
EP08-I02-S03 | Sub-issue | FE 14-01 | S1 | FE | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/169
EP08-I02-S04 | Sub-issue | Ca kiểm thử 14-01 | S1 | QA | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/170
EP08-I03 | Issue | Bắt buộc 期限種別 trên SKU và không suy mặc định | S1 | BE | 5 | 9.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/171
EP08-I04 | Issue | Quản lý traceability_lane và regulated_identifier | S1 | BE | 5 | 9.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/172
EP08-I05 | Issue | Dựng 14-02 顧客-SKU契約 và 顧客ヘッダ | S2 | FE | 13 | 24 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/173
EP08-I05-S01 | Sub-issue | Viết DD SCR-14 vùng 14-02 | S1 | SA | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/174
EP08-I05-S02 | Sub-issue | API hợp đồng và 顧客ヘッダ | S2 | BE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/175
EP08-I05-S03 | Sub-issue | FE 14-02 | S2 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/176
EP08-I05-S04 | Sub-issue | Ca kiểm thử 14-02 | S2 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/177
EP08-I06 | Issue | Xử lý delivery_window_rule 未確定 | S2 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/178
EP08-I07 | Issue | Dựng 14-03 仕入先 / 位置 / デバイス / 車両 | S2 | FE | 18 | 33.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/179
EP08-I07-S01 | Sub-issue | Viết DD SCR-14 vùng 14-03 (4 loại master) | S1 | SA | 4 | 7.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/180
EP08-I07-S02 | Sub-issue | API 仕入先 / 位置 / デバイス / 車両 | S2 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/181
EP08-I07-S03 | Sub-issue | FE 14-03 | S2 | FE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/182
EP08-I07-S04 | Sub-issue | Ca kiểm thử 14-03 | S2 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/183
EP08-I08 | Issue | Dựng 14-03 温度ポリシー版 | S1 | FE | 14 | 26 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/184
EP08-I08-S01 | Sub-issue | Viết DD SCR-14 vùng 14-03 温度ポリシー | S0 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/185
EP08-I08-S02 | Sub-issue | API 温度ポリシー版 | S1 | BE | 5 | 9.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/186
EP08-I08-S03 | Sub-issue | FE 温度ポリシー版 | S1 | FE | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/187
EP08-I08-S04 | Sub-issue | Ca kiểm thử biên 有効日 và duyệt chéo | S1 | QA | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/188
EP08-I09 | Issue | Dựng 14-04 承認キュー | S2 | FE | 14 | 26 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/189
EP08-I09-S01 | Sub-issue | Viết DD SCR-14 vùng 14-04 | S1 | SA | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/190
EP08-I09-S02 | Sub-issue | API hàng đợi duyệt | S2 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/191
EP08-I09-S03 | Sub-issue | FE 14-04 | S2 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/192
EP08-I09-S04 | Sub-issue | Ca kiểm thử tự duyệt và đồng thời | S2 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/193
EP08-I10 | Issue | Xử lý 依頼 閉鎖・再開 vị trí và IF設定 trong 14-04 | ST | BE | 11 | 20.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/194
EP08-I10-S01 | Sub-issue | Viết DD luồng 依頼 閉鎖・再開 và IF設定 | ST | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/195
EP08-I10-S02 | Sub-issue | BE áp 依頼 sau duyệt | ST | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/196
EP08-I10-S03 | Sub-issue | Ca kiểm thử 依頼 | ST | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/197
EP08-I11 | Issue | Duyệt reversal dòng giao đã nhận (M.5) | S3 | BE | 12 | 22 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/198
EP08-I11-S01 | Sub-issue | Viết DD luồng reversal dòng giao | S2 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/199
EP08-I11-S02 | Sub-issue | BE ghi reversal và cập nhật mốc | S3 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/200
EP08-I11-S03 | Sub-issue | Ca kiểm thử reversal và 日付逆転 | S3 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/201
EP08-I12 | Issue | Hiển thị lịch sử version và reversal chỉ đọc (M.4) | HARD | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/202
EP08-I13 | Issue | Dựng 14-06 保持ポリシー | S4 | FE | 13 | 24 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/203
EP08-I13-S01 | Sub-issue | Viết DD SCR-14 vùng 14-06 chính sách lưu | S3 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/204
EP08-I13-S02 | Sub-issue | API chính sách lưu | S4 | BE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/205
EP08-I13-S03 | Sub-issue | FE 14-06 chính sách lưu | S4 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/206
EP08-I13-S04 | Sub-issue | Ca kiểm thử đổi thời hạn | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/207
EP08-I14 | Issue | Áp hạn lưu nhóm luật định 労働関係記録 và 米 賞味 > 3 năm | S4 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/208
EP08-I15 | Issue | Đặt và gỡ Legal hold theo ca hoặc lô | S4 | BE | 14 | 26 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/209
EP08-I15-S01 | Sub-issue | Viết DD SCR-14 vùng 14-06 Legal hold | S3 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/210
EP08-I15-S02 | Sub-issue | BE Legal hold | S4 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/211
EP08-I15-S03 | Sub-issue | FE Legal hold trong 14-06 | S4 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/212
EP08-I15-S04 | Sub-issue | Ca kiểm thử hold và purge | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/213
EP08-I16 | Issue | Chạy B-08 lập danh sách purge hằng tháng và duyệt | S5 | BE | 14 | 26 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/214
EP08-I16-S01 | Sub-issue | Viết DD luồng lập và duyệt purge | S4 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/215
EP08-I16-S02 | Sub-issue | BE batch B-08 và duyệt | S5 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/216
EP08-I16-S03 | Sub-issue | FE purge 予定 trong 14-06 | S5 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/217
EP08-I16-S04 | Sub-issue | Ca kiểm thử B-08 | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/218
EP08-I17 | Issue | Chạy B-09 purge sau archive và so manifest | S5 | BE | 9 | 16.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/219
EP08-I17-S01 | Sub-issue | BE batch B-09 | S5 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/220
EP08-I17-S02 | Sub-issue | Ca kiểm thử purge an toàn | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/221
EP08-I18 | Issue | Kiểm phân quyền SCR-14 theo 職務 | ST | QA | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/222
EP08-I19 | Issue | Nạp dữ liệu master mẫu cho dev và test | S5 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/223
EP-09 | Epic | 外部IF: ERP, logger, bản đồ, IdP, mail, archive |  |  | 130 | 241 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/224
EP09-I01 | Issue | Dựng điểm nhận tệp SFTP managed cho ERP | S1 | Infra | 6 | 11 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/225
EP09-I01-S01 | Sub-issue | Viết DD điểm nhận SFTP | S0 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/226
EP09-I01-S02 | Sub-issue | IaC điểm nhận SFTP | S1 | Infra | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/227
EP09-I02 | Issue | Chạy B-01 nhập 入荷予定 từ ERP | S2 | BE | 11 | 20.5 | placeholder | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/228
EP09-I02-S01 | Sub-issue | Viết DD B-01 | S1 | SA | 3 | 5.5 | placeholder | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/229
EP09-I02-S02 | Sub-issue | BE batch B-01 | S2 | BE | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/230
EP09-I02-S03 | Sub-issue | Ca kiểm thử B-01 | S2 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/231
EP09-I03 | Issue | Chạy B-02 nhập 受注 hai tệp delta 10:30 và 13:30 | S2 | BE | 11 | 20.5 | placeholder | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/232
EP09-I03-S01 | Sub-issue | Viết DD B-02 | S1 | SA | 3 | 5.5 | placeholder | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/233
EP09-I03-S02 | Sub-issue | BE batch B-02 | S2 | BE | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/234
EP09-I03-S03 | Sub-issue | Ca kiểm thử B-02 | S2 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/235
EP09-I04 | Issue | Chạy B-03 xuất 入出庫・在庫結果 sang ERP lúc 23:30 | ST | BE | 12 | 22 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/236
EP09-I04-S01 | Sub-issue | Viết DD B-03 | ST | SA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/237
EP09-I04-S02 | Sub-issue | BE batch B-03 | ST | BE | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/238
EP09-I04-S03 | Sub-issue | Ca kiểm thử B-03 | ST | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/239
EP09-I05 | Issue | Dựng 14-05 外部IF連携状態 | S3 | FE | 14 | 26 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/240
EP09-I05-S01 | Sub-issue | Viết DD SCR-14 vùng 14-05 | S2 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/241
EP09-I05-S02 | Sub-issue | API trạng thái IF và 再実行 | S3 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/242
EP09-I05-S03 | Sub-issue | FE 14-05 | S3 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/243
EP09-I05-S04 | Sub-issue | Ca kiểm thử 14-05 | S3 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/244
EP09-I06 | Issue | Dựng cổng nhận tệp datalogger (IF-LOG-01) | ST | BE | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/245
EP09-I06-S01 | Sub-issue | Viết DD cổng nhận tệp logger | ST | SA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/246
EP09-I06-S02 | Sub-issue | BE cổng nhận tệp | ST | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/247
EP09-I07 | Issue | Dựng adapter bản đồ IF-MAP-01 | ST | BE | 8 | 15 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/248
EP09-I07-S01 | Sub-issue | Viết DD adapter bản đồ | ST | SA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/249
EP09-I07-S02 | Sub-issue | BE adapter Maps và cache | ST | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/250
EP09-I07-S03 | Sub-issue | Cấp tài nguyên Azure Maps | ST | Infra | 2 | 3.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/251
EP09-I08 | Issue | Kết nối Entra ID (IF-IDP-01) | S1 | BE | 13 | 24 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/252
EP09-I08-S01 | Sub-issue | Viết DD luồng SSO và đồng bộ vai | S0 | SA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/253
EP09-I08-S02 | Sub-issue | App registration và App roles | S1 | Infra | 3 | 5.5 | provisional | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/254
EP09-I08-S03 | Sub-issue | BE adapter OIDC | S1 | BE | 3 | 5.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/255
EP09-I08-S04 | Sub-issue | Ca kiểm thử token hết hạn và thu hồi vai | S1 | QA | 3 | 5.5 | provisional | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/256
EP09-I09 | Issue | Dựng hàng đợi mail và worker gửi lại (IF-MAIL-01) | S2 | BE | 11 | 20.5 | placeholder | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/257
EP09-I09-S01 | Sub-issue | Viết DD hàng đợi mail | S1 | SA | 3 | 5.5 | placeholder | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/258
EP09-I09-S02 | Sub-issue | BE mail_outbox và worker | S2 | BE | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/259
EP09-I09-S03 | Sub-issue | Ca kiểm thử thử lại và failed | S2 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/260
EP09-I10 | Issue | Dựng bộ phân giải người nhận và mẫu thông báo N-01〜N-16 | ST | BE | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/261
EP09-I11 | Issue | Dựng gửi lại mail failed từ 14-05 (F-21) | ST | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/262
EP09-I12 | Issue | Xuất archive RPT-14 (IF-ARCH-01) | S4 | BE | 9 | 16.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/263
EP09-I12-S01 | Sub-issue | Viết DD archive RPT-14 | S3 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/264
EP09-I12-S02 | Sub-issue | BE xuất archive | S4 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/265
EP09-I12-S03 | Sub-issue | Ca kiểm thử archive | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/266
EP09-I13 | Issue | Kiểm thử tích hợp IF với mock và hệ thật | ST | QA | 16 | 29.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/267
EP-01 | Epic | 入荷・検査・保管 — nhập hàng, kiểm, tạo lô |  |  | 146 | 270.5 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/268
EP01-I01 | Issue | Rà lại DD SCR-01 入荷検品 theo kiến trúc Azure | S1 | SA | 17 | 31.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/269
EP01-I01-S01 | Sub-issue | Viết lại §4 SCR-01 theo service + transaction trên App Service | S1 | SA | 5 | 9.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/270
EP01-I01-S02 | Sub-issue | Cập nhật ma trận quyền và thiết bị theo Entra ID | S1 | SA | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/271
EP01-I01-S03 | Sub-issue | Chuyển điểm kiểm thử §5.2 thành checklist test case | S1 | QA | 3 | 5.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/272
EP01-I01-S04 | Sub-issue | Chốt câu hỏi mở nhập hàng với PO / 品質オーナー | S1 | BrSE | 3 | 5.5 | placeholder | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/273
EP01-I01-S05 | Sub-issue | Review DD SCR-01 bản Azure | S1 | SA | 3 | 5.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/274
EP01-I02 | Issue | Tạo schema REC cho 入荷予定, dòng kiểm và 判定 | S2 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/275
EP01-I02-S01 | Sub-issue | Viết migration bảng REC + index | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/276
EP01-I02-S02 | Sub-issue | Test ràng buộc DB của REC | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/277
EP01-I03 | Issue | Đăng ký 入荷予定 và xem danh sách 予定 | S2 | BE | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/278
EP01-I03-S01 | Sub-issue | Test case 入荷予定登録 và View 1 | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/279
EP01-I03-S02 | Sub-issue | API tạo 入荷予定 + cảnh báo trùng | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/280
EP01-I03-S03 | Sub-issue | Màn View 1 và modal C | S2 | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/281
EP01-I04 | Issue | Lưu nháp 検査入力 với kiểm đủ trường P0 | S2 | BE | 14 | 26 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/282
EP01-I04-S01 | Sub-issue | Test case lưu nháp 検査入力 | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/283
EP01-I04-S02 | Sub-issue | API lưu nháp dòng kiểm | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/284
EP01-I04-S03 | Sub-issue | Màn View 2 trên tablet + quét mã | S2 | FE | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/285
EP01-I04-S04 | Sub-issue | Upload ảnh kiểm hàng | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/286
EP01-I05 | Issue | Kiểm dải nhiệt lúc nhập theo 版 ngưỡng hiệu lực và 一時温度帯 | S2 | BE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/287
EP01-I05-S01 | Sub-issue | Test case biên dải nhiệt lúc nhập | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/288
EP01-I05-S02 | Sub-issue | Module đánh giá dải và chọn dải áp dụng | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/289
EP01-I05-S03 | Sub-issue | Chọn 版 theo ngày và vị trí 入荷エリア | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/290
EP01-I05-S04 | Sub-issue | Hiển thị D-13 / D-14 và ticket D-18〜D-24 | S2 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/291
EP01-I06 | Issue | Phân biệt 消費期限 và 賞味期限 khi nhập hạn | S2 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/292
EP01-I06-S01 | Sub-issue | Test case hai loại hạn lúc nhập | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/293
EP01-I06-S02 | Sub-issue | Kiểm loại hạn ở service nhập | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/294
EP01-I06-S03 | Sub-issue | Nhãn và biểu tượng riêng cho loại hạn | S2 | FE | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/295
EP01-I07 | Issue | Kiểm truy xuất bắt buộc 米 / 牛 lúc nhập | S2 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/296
EP01-I07-S01 | Sub-issue | Test case truy xuất 米 / 牛 | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/297
EP01-I07-S02 | Sub-issue | Kiểm truy xuất ở service nhập | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/298
EP01-I07-S03 | Sub-issue | Ô 米産地 / 牛個体識別番号 theo lane | S2 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/299
EP01-I08 | Issue | Xác nhận 判定 idempotent theo request_id | S2 | BE | 15 | 28 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/300
EP01-I08-S01 | Sub-issue | Test case 判定確定 và idempotency | S2 | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/301
EP01-I08-S02 | Sub-issue | API 判定確定 + thứ tự khóa | S2 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/302
EP01-I08-S03 | Sub-issue | Màn View 3 判定 + hộp xác nhận | S2 | FE | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/303
EP01-I09 | Issue | Tạo lô bất biến, cách ly lúc nhập và ca 逸脱 nhập hàng | S2 | BE | 14 | 26 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/304
EP01-I09-S01 | Sub-issue | Test case tạo lô và cách ly lúc nhập | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/305
EP01-I09-S02 | Sub-issue | Migration bảng deviation_case / _lot / _entry | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/306
EP01-I09-S03 | Sub-issue | Service tạo lô và sự kiện tồn | S2 | BE | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/307
EP01-I09-S04 | Sub-issue | Helper tạo ca 逸脱 dùng chung | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/308
EP01-I10 | Issue | 分散承認 khi tổng lệch 報告数, maker ≠ checker trên PC | S2 | BE | 15 | 28 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/309
EP01-I10-S01 | Sub-issue | Test case 分散承認 | S2 | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/310
EP01-I10-S02 | Sub-issue | API lưu 承認待ち + outbox N-07 | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/311
EP01-I10-S03 | Sub-issue | API 承認 / 差戻し | S2 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/312
EP01-I10-S04 | Sub-issue | Màn View 4 trên PC | S2 | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/313
EP01-I11 | Issue | Nhập 返品 theo dòng giao vào 隔離 | ST | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/314
EP01-I11-S01 | Sub-issue | Test case 返品入荷 | ST | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/315
EP01-I11-S02 | Sub-issue | Kiểm 返品 theo dòng giao ở service | ST | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/316
EP01-I11-S03 | Sub-issue | Khung G-1 / G-2 và ô 返品 trên View 2 | ST | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/317
EP01-I12 | Issue | Xuất RPT-16 受入票 PDF | ST | BE | 7 | 13 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/318
EP01-I12-S01 | Sub-issue | Test case RPT-16 | ST | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/319
EP01-I12-S02 | Sub-issue | Sinh PDF RPT-16 + manifest | ST | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/320
EP01-I13 | Issue | Chạy kiểm thử SCR-01 trên môi trường test | ST | QA | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/321
EP01-I13-S01 | Sub-issue | Chạy bộ case chức năng SCR-01 | ST | QA | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/322
EP01-I13-S02 | Sub-issue | Chạy case quyền và phiên SCR-01 | ST | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/323
EP-02 | Epic | 在庫・ロット・三温度帯 — tồn kho, lô, vị trí theo dải nhiệt |  |  | 111 | 206 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/324
EP02-I01 | Issue | Tạo schema INV lõi: lô, phiên bản lô, tồn theo vị trí, sự kiện | S2 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/325
EP02-I01-S01 | Sub-issue | Migration bảng INV lõi | S2 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/326
EP02-I01-S02 | Sub-issue | Test bất biến INV | S2 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/327
EP02-I02 | Issue | Tra cứu tồn / lô đa điều kiện và chi tiết lô (SCR-02 View 1–2) | S3 | FE | 12 | 22 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/328
EP02-I02-S01 | Sub-issue | Viết DD SCR-02 (cả 3 view) | S2 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/329
EP02-I02-S02 | Sub-issue | Test case tra cứu và chi tiết lô | S3 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/330
EP02-I02-S03 | Sub-issue | API tìm kiếm + chi tiết lô | S3 | BE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/331
EP02-I03 | Issue | Ghi 移動 bất biến, idempotent, chặn tồn âm | S3 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/332
EP02-I03-S01 | Sub-issue | Test case 移動 | S3 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/333
EP02-I03-S02 | Sub-issue | Màn View 3 trên ハンディ | S3 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/334
EP02-I04 | Issue | Đề xuất vị trí lưu kho hợp lệ (FEFO, cùng SKU khác hạn) | ST | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/335
EP02-I04-S01 | Sub-issue | Test case đề xuất vị trí | ST | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/336
EP02-I05 | Issue | Chặn put-away / 移動 sai dải áp dụng, không tạo 逸脱 | S3 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/337
EP02-I05-S01 | Sub-issue | Test case dải áp dụng khi di chuyển | S3 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/338
EP02-I06 | Issue | Giữ dung lượng / 閉鎖 vị trí và gửi 閉鎖・再開依頼 | ST | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/339
EP02-I06-S01 | Sub-issue | Test case dung lượng và 閉鎖 | ST | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/340
EP02-I07 | Issue | 訂正 lô có phiên bản và duyệt người thứ hai | S4 | BE | 7 | 13 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/341
EP02-I07-S01 | Sub-issue | Test case 訂正 lô | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/342
EP02-I07-S02 | Sub-issue | Dialog 訂正 và khối 承認待ち | S4 | FE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/343
EP02-I08 | Issue | 訂正 牛個体識別番号 cho lô lane 牛 | S4 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/344
EP02-I08-S01 | Sub-issue | Test case 訂正 số cá thể bò | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/345
EP02-I09 | Issue | 訂正 有効期限: duyệt hai người, giải phóng 引当, giữ loại hạn | S4 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/346
EP02-I09-S01 | Sub-issue | Test case 訂正 有効期限 | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/347
EP02-I10 | Issue | Máy trạng thái 隔離: 隔離へ, 記録, リリース (SCR-03) | S3 | BE | 13 | 24 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/348
EP02-I10-S01 | Sub-issue | Viết DD SCR-03 | S2 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/349
EP02-I10-S02 | Sub-issue | Test case máy trạng thái 隔離 | S3 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/350
EP02-I10-S03 | Sub-issue | Màn SCR-03 danh sách + chi tiết | S3 | FE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/351
EP02-I11 | Issue | 廃棄依頼 và duyệt người thứ hai theo 位置 × ロット | S3 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/352
EP02-I11-S01 | Sub-issue | Migration disposal_request / _line | S3 | BE | 2 | 3.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/353
EP02-I11-S02 | Sub-issue | Test case 廃棄 hai người | S3 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/354
EP02-I12 | Issue | Dịch vụ cách ly dùng chung: nhiều 起因, giải phóng 引当 theo thứ tự khóa | S3 | BE | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/355
EP02-I12-S01 | Sub-issue | Viết DD luồng cách ly dùng chung | S2 | SA | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/356
EP02-I12-S02 | Sub-issue | Test đồng thời cách ly và 引当 | S3 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/357
EP02-I13 | Issue | Kiểm kê blind count: tạo task, đếm, nộp (SCR-16) | S4 | BE | 11 | 20.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/358
EP02-I13-S01 | Sub-issue | Viết DD SCR-16 | S3 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/359
EP02-I13-S02 | Sub-issue | Test case blind count | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/360
EP02-I13-S03 | Sub-issue | Màn đếm trên ハンディ | S4 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/361
EP02-I14 | Issue | Điều chỉnh chênh lệch kiểm kê: lý do, ngưỡng có version, maker–checker | ST | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/362
EP02-I14-S01 | Sub-issue | Test case điều chỉnh kiểm kê | ST | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/363
EP02-I14-S02 | Sub-issue | Màn View 3 đối chiếu + duyệt | ST | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/364
EP02-I15 | Issue | 返品 vào kho qua 隔離 (D-B) phía tồn kho | S4 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/365
EP02-I15-S01 | Sub-issue | Viết DD luồng 返品 vào 隔離 | S3 | SA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/366
EP02-I15-S02 | Sub-issue | Test case 返品 phía tồn kho | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/367
EP02-I16 | Issue | Chốt câu hỏi mở tồn kho / kiểm kê với PO | HARD | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/368
EP02-I17 | Issue | Chạy kiểm thử SCR-02 / 03 / 16 trên môi trường test | ST | QA | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/369
EP-05 | Epic | 温度監視・逸脱・HACCP — giám sát nhiệt, ca 逸脱, hồ sơ HACCP |  |  | 184 | 341 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/370
EP05-I01 | Issue | Rà lại DD SCR-09 温度監視 theo kiến trúc Azure | S3 | SA | 13 | 24 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/371
EP05-I01-S01 | Sub-issue | Viết lại §4 SCR-09 theo worker bất đồng bộ | S3 | SA | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/372
EP05-I01-S02 | Sub-issue | Cập nhật quyền đọc theo 職務 ở API | S3 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/373
EP05-I01-S03 | Sub-issue | Chuyển TP SCR-09 thành checklist test case | S3 | QA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/374
EP05-I01-S04 | Sub-issue | Review DD SCR-09 bản Azure | S3 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/375
EP05-I02 | Issue | Chốt câu hỏi khách về logger CSV và mức HACCP | S5 | BrSE | 4 | 7.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/376
EP05-I03 | Issue | Tạo schema TMP: tệp nhập, reading, event, alarm, haccp_task | S4 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/377
EP05-I03-S01 | Sub-issue | Migration bảng TMP + partition | S4 | BE | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/378
EP05-I03-S02 | Sub-issue | Test ràng buộc TMP | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/379
EP05-I04 | Issue | Nhập CSV logger idempotent theo SHA-256 (SCR-09 View 2) | S4 | BE | 20 | 37 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/380
EP05-I04-S01 | Sub-issue | Test case nhập CSV | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/381
EP05-I04-S02 | Sub-issue | API nhận tệp + SHA-256 + xếp hàng | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/382
EP05-I04-S03 | Sub-issue | Worker xử lý tệp + kiểm dòng | S4 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/383
EP05-I04-S04 | Sub-issue | Hàng đợi và worker trên Azure | S4 | Infra | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/384
EP05-I04-S05 | Sub-issue | Màn View 2 kết quả nhập (PC + tablet) | S4 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/385
EP05-I05 | Issue | Đánh giá ngưỡng theo 版 và phạm vi zone / lô có ticket | S4 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/386
EP05-I05-S01 | Sub-issue | Test case đánh giá ngưỡng | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/387
EP05-I05-S02 | Sub-issue | Service đánh giá reading theo phạm vi | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/388
EP05-I06 | Issue | Đợt lệch và alarm theo thời lượng, khoảng trống không cắt đợt | S4 | BE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/389
EP05-I06-S01 | Sub-issue | Test case đợt lệch / alarm | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/390
EP05-I06-S02 | Sub-issue | Engine đợt lệch theo thời lượng | S4 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/391
EP05-I06-S03 | Sub-issue | Phát hiện ロガー欠落 và 記録到着 | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/392
EP05-I07 | Issue | Lô ảnh hưởng của alarm, ca 逸脱 và cách ly theo thứ tự khóa | S4 | BE | 13 | 24 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/393
EP05-I07-S01 | Sub-issue | Test case lô ảnh hưởng và cách ly | S4 | QA | 4 | 7.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/394
EP05-I07-S02 | Sub-issue | Phát lại stock_event lấy lô trong cửa sổ đợt | S4 | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/395
EP05-I07-S03 | Sub-issue | Tạo ca + cách ly trong giao dịch nhập | S4 | BE | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/396
EP05-I08 | Issue | Gửi mail N-01 sau mỗi lần nhập có alarm mới hoặc 未評価 | S4 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/397
EP05-I08-S01 | Sub-issue | Test case N-01 | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/398
EP05-I08-S02 | Sub-issue | Ghi outbox N-01 trong giao dịch nhập | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/399
EP05-I09 | Issue | Ghi review alarm đầu tiên và đánh dấu quá hạn 15 phút | S4 | BE | 11 | 20.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/400
EP05-I09-S01 | Sub-issue | Test case review alarm | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/401
EP05-I09-S02 | Sub-issue | API review alarm | S4 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/402
EP05-I09-S03 | Sub-issue | Danh sách alarm + panel chi tiết / review | S4 | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/403
EP05-I10 | Issue | Dashboard giám sát nhiệt độ (SCR-09 View 1) | S4 | FE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/404
EP05-I10-S01 | Sub-issue | API đọc dashboard gộp phía server | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/405
EP05-I10-S02 | Sub-issue | Test case dashboard | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/406
EP05-I11 | Issue | Cảnh báo 取込遅延 theo logger (B-05, A-8) | S5 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/407
EP05-I11-S01 | Sub-issue | Job timer B-05 trên Functions | S5 | Infra | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/408
EP05-I11-S02 | Sub-issue | Logic phát hiện thiếu tệp + A-8 | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/409
EP05-I11-S03 | Sub-issue | Test case 取込遅延 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/410
EP05-I12 | Issue | Cờ 要確認 chặn 引当 / 出荷確認 khi mất dữ liệu nhiệt | S5 | BE | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/411
EP05-I12-S01 | Sub-issue | Test case mất dữ liệu nhiệt | S5 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/412
EP05-I12-S02 | Sub-issue | Gắn / gỡ cờ lô theo khoảng trống | S5 | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/413
EP05-I13 | Issue | Đánh giá tăng dần cho khối lượng 2,5 triệu reading | S5 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/414
EP05-I13-S01 | Sub-issue | Tối ưu truy vấn ngữ cảnh device | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/415
EP05-I13-S02 | Sub-issue | Đo tải nhập CSV | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/416
EP05-I14 | Issue | Xuất RPT-17 温度記録表 | S5 | BE | 7 | 13 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/417
EP05-I14-S01 | Sub-issue | Test case RPT-17 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/418
EP05-I14-S02 | Sub-issue | Sinh RPT-17 | S5 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/419
EP05-I15 | Issue | Quản lý ca 逸脱: điều tra, 再測定 品温, chứng cứ, 決定案 (SCR-10) | S5 | BE | 15 | 28 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/420
EP05-I15-S01 | Sub-issue | Viết DD SCR-10 | S4 | SA | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/421
EP05-I15-S02 | Sub-issue | Test case ca 逸脱 | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/422
EP05-I15-S03 | Sub-issue | Màn danh sách + chi tiết ca | S5 | FE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/423
EP05-I16 | Issue | Vai trò theo 重大度 và điều kiện đóng ca | S5 | BE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/424
EP05-I16-S01 | Sub-issue | Test case vai trò và đóng ca | S5 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/425
EP05-I17 | Issue | Hàng đợi HACCP欠落 và batch B-07 phát hiện thiếu hồ sơ | S5 | BE | 12 | 22 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/426
EP05-I17-S01 | Sub-issue | Viết DD luồng B-07 và hàng đợi | S4 | SA | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/427
EP05-I17-S02 | Sub-issue | Test case hàng đợi HACCP | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/428
EP05-I17-S03 | Sub-issue | Job timer B-07 | S5 | Infra | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/429
EP05-I18 | Issue | 日次確認 / 月次確認 với maker ≠ checker | S5 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/430
EP05-I18-S01 | Sub-issue | Test case 日次 / 月次確認 | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/431
EP05-I19 | Issue | Nhập hồ sơ 衛生 và 来訪者・ドライバー trên tablet chung (SCR-10 View 4) | S5 | FE | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/432
EP05-I19-S01 | Sub-issue | Migration + API sanitation / visitor | S5 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/433
EP05-I19-S02 | Sub-issue | Test case View 4 | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/434
EP05-I20 | Issue | Xuất RPT-18 逸脱・隔離記録 cho một ca | S5 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/435
EP05-I20-S01 | Sub-issue | Test case RPT-18 | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/436
EP05-I21 | Issue | Chạy kiểm thử SCR-09 / SCR-10 trên môi trường test | S6 | QA | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/437
EP05-I21-S01 | Sub-issue | Chạy case SCR-09 | S6 | QA | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/438
EP05-I21-S02 | Sub-issue | Chạy case SCR-10 và HACCP | S6 | QA | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/439
EP-03 | Epic | 有効期限管理・出荷・ピッキング・POD (E3) |  |  | 305 | 565.5 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/440
EP03-I01 | Issue | Chỉnh DD SCR-05 cho hệ đích Azure | S2 | SA | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/441
EP03-I01-S01 | Sub-issue | Viết lại §4 của DD SCR-05 theo service App Service | S2 | SA | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/442
EP03-I01-S02 | Sub-issue | Chạy predict-risks cho cây 引当 và khóa | S2 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/443
EP03-I01-S03 | Sub-issue | Review DD SCR-05 và chốt DoR | S2 | BrSE | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/444
EP03-I02 | Issue | Chỉnh DD SCR-06 cho hệ đích Azure | S2 | SA | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/445
EP03-I02-S01 | Sub-issue | Viết lại §4 DD SCR-06 theo service App Service | S2 | SA | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/446
EP03-I02-S02 | Sub-issue | Chạy predict-risks cho D-A và 積込取消 | S2 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/447
EP03-I02-S03 | Sub-issue | Review DD SCR-06 và chốt DoR | S2 | BrSE | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/448
EP03-I03 | Issue | Chỉnh DD SCR-08 phần POD / hàng đợi / đồng bộ | S3 | SA | 10 | 18.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/449
EP03-I03-S01 | Sub-issue | Viết lại §4.4, §4.6 DD SCR-08 theo service + Blob | S3 | SA | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/450
EP03-I03-S02 | Sub-issue | Chạy predict-risks cho offline / idempotency POD | S3 | SA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/451
EP03-I03-S03 | Sub-issue | Review DD SCR-08 phần POD và chốt DoR | S3 | BrSE | 2 | 3.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/452
EP03-I04 | Issue | Dựng schema OUT_DB cho luồng xuất | S2 | BE | 12 | 22 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/453
EP03-I04-S01 | Sub-issue | Soạn CR OUT_DB: idempotency_key và mức khóa (R)(D)(4) | S1 | BrSE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/454
EP03-I04-S02 | Sub-issue | Viết migration bảng xuất và index | S2 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/455
EP03-I04-S03 | Sub-issue | Viết test ràng buộc DB xuất | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/456
EP03-I04-S04 | Sub-issue | Review schema OUT_DB | S2 | SA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/457
EP03-I05 | Issue | Nhập dòng 受注 tay và kiểm master / trùng tham chiếu | S3 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/458
EP03-I05-S01 | Sub-issue | Viết DD SCR-04 — nhập / sửa / xóa dòng 未確定 | S2 | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/459
EP03-I06 | Issue | 受注確定 một dòng / 一括 kèm giờ cắt 16:00 và kích hoạt 引当 | S3 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/460
EP03-I06-S01 | Sub-issue | Viết DD SCR-04 — 受注確定 và 一括確定 | S2 | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/461
EP03-I07 | Issue | Màn SCR-04 View 2: duyệt dòng từ 2 tệp ERP delta | ST | FE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/462
EP03-I07-S01 | Sub-issue | Viết DD SCR-04 — View 2 dòng tệp ERP | ST | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/463
EP03-I08 | Issue | Engine 引当 ở server: loại trừ 6 mức, FEFO/FIFO, khóa nguyên tử | S3 | BE | 20 | 37 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/464
EP03-I08-S01 | Sub-issue | Viết TC engine 引当 (thứ tự loại trừ, FEFO, đồng thời) | S3 | QA | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/465
EP03-I08-S02 | Sub-issue | Cài hàm đánh giá thuần evaluateCandidates | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/466
EP03-I08-S03 | Sub-issue | Cài giao dịch 引当 với khóa và kiểm lại | S3 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/467
EP03-I08-S04 | Sub-issue | Ghi kết quả 引当 vào idempotency và sự kiện | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/468
EP03-I08-S05 | Sub-issue | Review code engine 引当 | S3 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/469
EP03-I09 | Issue | 日付逆転: so hạn với lần giao 受領済 gần nhất theo cặp khách × SKU | S3 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/470
EP03-I09-S01 | Sub-issue | Viết TC 日付逆転 nguồn (a) | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/471
EP03-I09-S02 | Sub-issue | Cài tính mốc R4 nguồn (a) và so sánh | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/472
EP03-I09-S03 | Sub-issue | Review 日付逆転 với ADR-004 | S3 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/473
EP03-I10 | Issue | 日付逆転: thêm nguồn (b)(c) đơn khác cùng cặp đang 引当 / 積込 / đang chở | S4 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/474
EP03-I10-S01 | Sub-issue | Viết TC nguồn (b)(c) và công tắc | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/475
EP03-I10-S02 | Sub-issue | Cài nguồn (b)(c) và tham số chọn nguồn | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/476
EP03-I11 | Issue | 消費期限 chặn cứng / 賞味期限 chỉ cảnh báo trong 引当 và lúc 積込・出荷 | S3 | BE | 7 | 13 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/477
EP03-I11-S01 | Sub-issue | Viết TC 賞味 / 消費 ở 引当 và 積込・出荷 | S3 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/478
EP03-I11-S02 | Sub-issue | Cài E1 và event use_by_block giao dịch riêng | S3 | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/479
EP03-I11-S03 | Sub-issue | Cài cảnh báo 賞味 theo cấu hình | S3 | BE | 1 | 2 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/480
EP03-I12 | Issue | 配送ウィンドウ 1/3・1/2 theo 要求日 và lưu bằng chứng tính | S3 | BE | 7 | 13 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/481
EP03-I12-S01 | Sub-issue | Viết TC 1/3・1/2 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/482
EP03-I12-S02 | Sub-issue | Cài E4 và lưu bằng chứng | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/483
EP03-I12-S03 | Sub-issue | Đưa làm tròn 1/3・1/2 thành tham số cấu hình | S3 | BE | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/484
EP03-I13 | Issue | Chặn lô 牛 確認待ち ở 引当 và lúc 積込・出荷 | S3 | BE | 7 | 13 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/485
EP03-I13-S01 | Sub-issue | Viết TC lô 牛 確認待ち | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/486
EP03-I13-S02 | Sub-issue | Cài E3b trong hàm đánh giá | S3 | BE | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/487
EP03-I13-S03 | Sub-issue | Cài chặn M_OUT-65 ở 積込確認 / 積込完了 / 出荷確認 | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/488
EP03-I14 | Issue | 温度帯: loại lô lệch dải ở 引当 và kiểm 3 giá trị ở 積込確認 | S3 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/489
EP03-I14-S01 | Sub-issue | Viết TC 温度帯 ở 引当 và 積込確認 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/490
EP03-I14-S02 | Sub-issue | Cài appliedBand và E2 | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/491
EP03-I14-S03 | Sub-issue | Cài kiểm 3 giá trị + ticket 出荷票 ở C-11 | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/492
EP03-I15 | Issue | 解放 → 再引当: giải phóng khi lô 隔離 / 訂正 / 棚卸し và F-4 | S3 | BE | 13 | 24 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/493
EP03-I15-S01 | Sub-issue | Viết TC 解放 và F-4 | S3 | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/494
EP03-I15-S02 | Sub-issue | Cài release theo giao thức khóa 4.5 | S3 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/495
EP03-I15-S03 | Sub-issue | Cài API F-4 再引当 | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/496
EP03-I16 | Issue | 受注取消 trước picking (F-5) và job phục hồi dòng kẹt 処理中 | ST | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/497
EP03-I16-S01 | Sub-issue | Viết TC F-5 và job R12 | ST | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/498
EP03-I16-S02 | Sub-issue | Cài API F-5 受注取消 | ST | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/499
EP03-I16-S03 | Sub-issue | Cài job R12 処理中 timeout | ST | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/500
EP03-I17 | Issue | Màn SCR-05 ロット引当結果確認 (xem kết quả, đánh giá lô, F-4 / F-5) | ST | FE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/501
EP03-I17-S01 | Sub-issue | Dựng màn SCR-05 vùng A〜D | ST | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/502
EP03-I17-S02 | Sub-issue | Nối F-4 / F-5 và thông điệp E-1 | ST | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/503
EP03-I17-S03 | Sub-issue | Kiểm E2E SCR-05 | ST | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/504
EP03-I18 | Issue | タスク一覧 và quét GS1-128 / JAN / ITF, lần quét đầu → picked | S3 | BE | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/505
EP03-I18-S01 | Sub-issue | Viết TC quét và タスク一覧 | S3 | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/506
EP03-I18-S02 | Sub-issue | Cài bộ tách mã vạch | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/507
EP03-I18-S03 | Sub-issue | Cài API タスク一覧 và lần quét đầu | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/508
EP03-I19 | Issue | 積込確認 (C-11) theo thứ tự kiểm OUT_DB R7 | S3 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/509
EP03-I19-S01 | Sub-issue | Viết TC 積込確認 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/510
EP03-I19-S02 | Sub-issue | Cài API 積込確認 | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/511
EP03-I20 | Issue | 積込完了 (車両) và ghi seal một lần cho xe × chuyến | S3 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/512
EP03-I20-S01 | Sub-issue | Viết TC 積込完了 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/513
EP03-I20-S02 | Sub-issue | Cài API 積込完了 + seal | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/514
EP03-I21 | Issue | 出荷前チェック 記録 / 再測定 theo ngưỡng có version và tạo 逸脱 | S3 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/515
EP03-I21-S01 | Sub-issue | Viết TC 出荷前チェック | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/516
EP03-I21-S02 | Sub-issue | Cài API 記録 / 再測定 | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/517
EP03-I21-S03 | Sub-issue | Chốt giao dịch cách ly lô khi 貨物温度 NG | S3 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/518
EP03-I22 | Issue | 貨物温度 NG khi task loaded: bắt 積込取消 rồi mới 解放 (H-7) | S4 | BE | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/519
EP03-I22-S01 | Sub-issue | Viết TC nhánh 貨物温度 NG khi loaded | S4 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/520
EP03-I22-S02 | Sub-issue | Cài nhánh NG theo PA A | S4 | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/521
EP03-I23 | Issue | 出荷確認: trừ tồn đúng một lần (D-A) | S4 | BE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/522
EP03-I23-S01 | Sub-issue | Viết TC 出荷確認 một lần | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/523
EP03-I23-S02 | Sub-issue | Cài API 出荷確認 | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/524
EP03-I23-S03 | Sub-issue | Soạn CR INV_DB: UNIQUE index stock_event 出荷 theo task | S3 | BrSE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/525
EP03-I23-S04 | Sub-issue | Review D-A trước release | S4 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/526
EP03-I24 | Issue | 積込取消: dỡ hàng, vô hiệu seal, đưa task khác về 出荷再確認 | S4 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/527
EP03-I24-S01 | Sub-issue | Viết TC 積込取消 | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/528
EP03-I24-S02 | Sub-issue | Cài API 積込取消 | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/529
EP03-I25 | Issue | Chặn 出発 khi lô đã 出荷確認 bị 隔離 / recall và cho 出荷取消 trước 出発 (H-5) | S4 | BE | 7 | 13 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/530
EP03-I25-S01 | Sub-issue | Viết TC recall × 出荷確認 × 出発 | S4 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/531
EP03-I25-S02 | Sub-issue | Cài 出荷取消 (đảo stock_event) | S4 | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/532
EP03-I25-S03 | Sub-issue | Thêm kiểm lô 隔離 vào cổng 出発 | S4 | BE | 1 | 2 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/533
EP03-I26 | Issue | Màn SCR-06 ba view (ハンディ View 1〜2, tablet View 3) | ST | FE | 11 | 20.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/534
EP03-I26-S01 | Sub-issue | Dựng View 1〜2 cho ハンディ | ST | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/535
EP03-I26-S02 | Sub-issue | Dựng View 3 cho tablet | ST | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/536
EP03-I26-S03 | Sub-issue | Kiểm E2E / a11y SCR-06 | ST | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/537
EP03-I27 | Issue | Sổ pod_sync_receipt: idempotency bản ghi tài xế, N-13, B-16 | S3 | BE | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/538
EP03-I27-S01 | Sub-issue | Viết TC idempotency và B-16 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/539
EP03-I27-S02 | Sub-issue | Cài sổ receipt và khung xử lý từng bản ghi | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/540
EP03-I27-S03 | Sub-issue | Cài N-13 và job B-16 | S3 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/541
EP03-I28 | Issue | OfflineQueue mã hóa chỉ ở app tài xế (IndexedDB + WebCrypto) | S3 | FE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/542
EP03-I28-S01 | Sub-issue | Viết TC hàng đợi offline | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/543
EP03-I28-S02 | Sub-issue | Cài store IndexedDB và mã hóa | S3 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/544
EP03-I28-S03 | Sub-issue | Cài tuổi hàng đợi, phạm vi tài xế, logout | S3 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/545
EP03-I28-S04 | Sub-issue | Review mã hóa hàng đợi với セキュリティオーナー | S3 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/546
EP03-I29 | Issue | Đồng bộ tự động hàng đợi tài xế, phân loại synced / duplicate / refused / retry | S4 | FE | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/547
EP03-I29-S01 | Sub-issue | Viết TC đồng bộ | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/548
EP03-I29-S02 | Sub-issue | Cài bộ lập lịch đồng bộ + mutex | S4 | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/549
EP03-I29-S03 | Sub-issue | Cài API sync xử lý từng bản ghi một giao dịch | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/550
EP03-I30 | Issue | POD theo dòng 受注: pod, pod_line, shipment_line, không trừ tồn | S4 | BE | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/551
EP03-I30-S01 | Sub-issue | Viết TC POD theo dòng | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/552
EP03-I30-S02 | Sub-issue | Cài registerPod và pod_line | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/553
EP03-I30-S03 | Sub-issue | Ghi shipment_line OUT từ POD | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/554
EP03-I30-S04 | Sub-issue | Review phát hành cùng D-A | S4 | SA | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/555
EP03-I31 | Issue | Bằng chứng POD theo hợp đồng 車上渡し / 軒先渡し và snapshot lúc server nhận | S4 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/556
EP03-I31-S01 | Sub-issue | Viết TC bằng chứng theo hợp đồng | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/557
EP03-I31-S02 | Sub-issue | Cài kiểm bằng chứng và snapshot | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/558
EP03-I32 | Issue | Upload tệp POD idempotent lên Blob với SHA-256 | S4 | BE | 6 | 11 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/559
EP03-I32-S01 | Sub-issue | Cài API attachments + kiểm SHA-256 | S4 | BE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/560
EP03-I32-S02 | Sub-issue | Tính SHA-256 và gửi tệp từ hàng đợi | S4 | FE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/561
EP03-I33 | Issue | Màn SCR-08 POD登録 và vùng đồng bộ (375 px) | ST | FE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/562
EP03-I33-S01 | Sub-issue | Dựng View 2 POD登録 | ST | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/563
EP03-I33-S02 | Sub-issue | Dựng header và vùng đồng bộ | ST | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/564
EP03-I33-S03 | Sub-issue | Kiểm E2E offline SCR-08 POD | ST | QA | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/565
EP03-I34 | Issue | POD訂正 bằng 版 mới ở SCR-12 (7 ngày, chỉ thêm bằng chứng) | S4 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/566
EP03-I34-S01 | Sub-issue | Viết DD SCR-12 — POD訂正 (View H) | S3 | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/567
EP03-I35 | Issue | Claim gắn dòng giao / lô / bằng chứng, trạng thái tách xử lý tồn | S4 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/568
EP03-I35-S01 | Sub-issue | Viết DD SCR-12 — claim (View G) | S3 | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/569
EP-04 | Epic | ルート計画・拘束時間 (E4) |  |  | 203 | 376.5 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/570
EP04-I01 | Issue | Chỉnh DD SCR-07 cho hệ đích Azure và chốt tham số 【仮定】 | S1 | SA | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/571
EP04-I01-S01 | Sub-issue | Viết lại §4 DD SCR-07 theo service | S1 | SA | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/572
EP04-I01-S02 | Sub-issue | Chạy predict-risks cho 公開 và engine 拘束時間 | S1 | SA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/573
EP04-I01-S03 | Sub-issue | Gửi lô câu hỏi 法務 Q-DD07-01 / 02, Q-A-01, Q30, Q63 | S1 | BrSE | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/574
EP04-I01-S04 | Sub-issue | Review DD SCR-07 và chốt DoR | S1 | BrSE | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/575
EP04-I02 | Issue | Chỉnh DD SCR-08 phần lịch trình, シール確認, 出発 / 帰着, 例外事象 | ST | SA | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/576
EP04-I02-S01 | Sub-issue | Viết lại 4.1〜4.3, 4.5 DD SCR-08 theo service | ST | SA | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/577
EP04-I02-S02 | Sub-issue | Review DD SCR-08 phần chuyến và chốt DoR | ST | BrSE | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/578
EP04-I03 | Issue | Dựng schema DSP_DB và CR thêm 帰着予定 | S2 | BE | 10 | 18.5 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/579
EP04-I03-S01 | Sub-issue | Soạn CR DSP_DB: 帰着予定 và cột kiểm giờ thiết bị | S1 | BrSE | 2 | 3.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/580
EP04-I03-S02 | Sub-issue | Viết migration DSP_DB | S2 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/581
EP04-I03-S03 | Sub-issue | Viết test ràng buộc DSP_DB | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/582
EP04-I03-S04 | Sub-issue | Review schema DSP_DB | S2 | SA | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/583
EP04-I04 | Issue | ルール版 拘束時間 2024 kèm nguồn pháp lý và cờ xác minh | S2 | BE | 12 | 22 | firm | In Progress | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/584
EP04-I04-S01 | Sub-issue | Lập bảng đối chiếu giá trị ↔ nguồn pháp lý để 法務 ký | S1 | BrSE | 3 | 5.5 | firm | Done | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/585
EP04-I04-S02 | Sub-issue | Viết seed ルール版 2024-04 và loader | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/586
EP04-I04-S03 | Sub-issue | Thêm tham số 【仮定】 nhóm dispatch_duty | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/587
EP04-I04-S04 | Sub-issue | Viết TC chọn ルール版 và cờ 未検証 | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/588
EP04-I05 | Issue | 公開: server tự tính lại, không tin nháp, chặn ルール版 未検証 ở prod | S2 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/589
EP04-I05-S01 | Sub-issue | Viết TC 公開 gồm gọi API trực tiếp | S2 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/590
EP04-I05-S02 | Sub-issue | Cài publish với thứ tự kiểm 4.4 | S2 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/591
EP04-I05-S03 | Sub-issue | Cài guard M_DSP-46 theo môi trường | S2 | BE | 1 | 2 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/592
EP04-I05-S04 | Sub-issue | Review publish (bảo mật + pháp lý) | S2 | SA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/593
EP04-I06 | Issue | Khóa tài xế và tính lại lũy kế 拘束時間 trong giao dịch 公開 (H-6) | S2 | BE | 8 | 15 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/594
EP04-I06-S01 | Sub-issue | Viết TC 2 phiên 公開 cùng tài xế | S2 | QA | 4 | 7.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/595
EP04-I06-S02 | Sub-issue | Cài khóa tài xế và tính lại lũy kế | S2 | BE | 4 | 7.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/596
EP04-I07 | Issue | Tạo / tạo lại nháp route từ đơn 引当済 (ルート作成) | S3 | BE | 12 | 22 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/597
EP04-I07-S01 | Sub-issue | Viết TC ルート作成 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/598
EP04-I07-S02 | Sub-issue | Cài makeDraft (phán định đơn, ETA, 帰着予定) | S3 | BE | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/599
EP04-I07-S03 | Sub-issue | Nối IF-MAP-01 qua port và cache cặp điểm | S3 | BE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/600
EP04-I08 | Issue | 連続運転 ≤ 4 h và tự chèn 休息 30 phút trước khi vượt | S3 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/601
EP04-I08-S01 | Sub-issue | Viết TC 連続運転 / 休息 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/602
EP04-I08-S02 | Sub-issue | Cài chèn 休息 và R-HR-09 | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/603
EP04-I09 | Issue | Sửa nháp, 版 n+1, đơn sau 14:00 và chặn bỏ stop đã giao | ST | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/604
EP04-I09-S01 | Sub-issue | Viết TC 版 n+1 và bỏ stop đã giao | ST | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/605
EP04-I09-S02 | Sub-issue | Cài editDraft và newVersion | ST | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/606
EP04-I09-S03 | Sub-issue | Cài N-12 cho đơn sau 14:00 | ST | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/607
EP04-I10 | Issue | Khung engine 拘束時間: dựng timeline, gộp kết quả, 未判定, API チェック実行 | S3 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/608
EP04-I10-S01 | Sub-issue | Viết TC gộp kết quả và 未判定 | S3 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/609
EP04-I10-S02 | Sub-issue | Cài khung engine và interface quy tắc | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/610
EP04-I10-S03 | Sub-issue | Cài API checkDuty và lưu route_duty_check | S3 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/611
EP04-I11 | Issue | R-HR-01/02: 1日拘束 13 h / tối đa 15 h, cửa sổ 24 h từ 始業 | S5 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/612
EP04-I11-S01 | Sub-issue | Viết TC biên cho R-HR-01/02 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/613
EP04-I11-S02 | Sub-issue | Cài quy tắc R-HR-01/02 trong engine | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/614
EP04-I11-S03 | Sub-issue | Review quy tắc R-HR-01/02 với bảng 3.4 | S5 | SA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/615
EP04-I12 | Issue | R-HR-04/05: 拘束 tháng 284 h và năm 3,300 h | S5 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/616
EP04-I12-S01 | Sub-issue | Viết TC biên cho R-HR-04/05 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/617
EP04-I12-S02 | Sub-issue | Cài quy tắc R-HR-04/05 trong engine | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/618
EP04-I12-S03 | Sub-issue | Review quy tắc R-HR-04/05 với bảng 3.4 | S5 | SA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/619
EP04-I13 | Issue | R-HR-06: 休息期間 ≥ 9 h (mục tiêu 11 h) | S5 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/620
EP04-I13-S01 | Sub-issue | Viết TC biên cho R-HR-06 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/621
EP04-I13-S02 | Sub-issue | Cài quy tắc R-HR-06 trong engine | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/622
EP04-I13-S03 | Sub-issue | Review quy tắc R-HR-06 với bảng 3.4 | S5 | SA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/623
EP04-I14 | Issue | R-HR-07/08: 運転 trung bình 2 ngày 9 h và 2 tuần 44 h | S5 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/624
EP04-I14-S01 | Sub-issue | Viết TC biên cho R-HR-07/08 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/625
EP04-I14-S02 | Sub-issue | Cài quy tắc R-HR-07/08 trong engine | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/626
EP04-I14-S03 | Sub-issue | Review quy tắc R-HR-07/08 với bảng 3.4 | S5 | SA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/627
EP04-I15 | Issue | R-HR-10: 時間外 năm ≤ 960 h (bộ đếm riêng với 拘束) | S5 | BE | 8 | 15 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/628
EP04-I15-S01 | Sub-issue | Viết TC biên cho R-HR-10 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/629
EP04-I15-S02 | Sub-issue | Cài quy tắc R-HR-10 trong engine | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/630
EP04-I15-S03 | Sub-issue | Review quy tắc R-HR-10 với bảng 3.4 | S5 | SA | 2 | 3.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/631
EP04-I16 | Issue | Đầu vào 始業 / 終業 từ 出発 / 帰着 và số dư đầu kỳ cho timeline | S5 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/632
EP04-I16-S01 | Sub-issue | Viết TC timeline từ 出発 / 帰着 | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/633
EP04-I16-S02 | Sub-issue | Cài timeline builder | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/634
EP04-I16-S03 | Sub-issue | Cài nạp CSV số dư và 14 ngày | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/635
EP04-I17 | Issue | Kiểm hợp lý giờ thiết bị (CK-1〜CK-4) cho 出発 / 帰着 / POD / 例外事象 | S5 | BE | 6 | 11 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/636
EP04-I17-S01 | Sub-issue | Viết TC giờ thiết bị | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/637
EP04-I17-S02 | Sub-issue | Cài CK-1〜CK-4 và cờ suspect | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/638
EP04-I18 | Issue | シール番号確認 trên app tài xế (online / offline) và báo lệch | S4 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/639
EP04-I18-S01 | Sub-issue | Viết TC シール確認 | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/640
EP04-I18-S02 | Sub-issue | Cài recordSealCheck | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/641
EP04-I18-S03 | Sub-issue | Cài B-12 và bản ghi seal_check offline | S4 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/642
EP04-I19 | Issue | 出発 / 帰着 trên app tài xế, đổi route.status, cổng 出荷確認 | S4 | BE | 9 | 16.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/643
EP04-I19-S01 | Sub-issue | Viết TC 出発 / 帰着 | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/644
EP04-I19-S02 | Sub-issue | Cài recordTripMovement | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/645
EP04-I19-S03 | Sub-issue | Cài B-10 / B-11 và điều kiện enabled theo cache | S4 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/646
EP04-I20 | Issue | 例外事象 bất biến và 計画超過スロット tách khỏi kết quả tuân thủ | S5 | BE | 11 | 20.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/647
EP04-I20-S01 | Sub-issue | Viết TC 例外事象 và slot | S5 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/648
EP04-I20-S02 | Sub-issue | Cài registerException và R-HR-13 | S5 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/649
EP04-I20-S03 | Sub-issue | Dựng SCR-08 View 3 例外事象登録 | S5 | FE | 5 | 9.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/650
EP04-I21 | Issue | Màn SCR-07 View 1 ルート作成 và View 3 公開・版履歴 | ST | FE | 11 | 20.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/651
EP04-I21-S01 | Sub-issue | Dựng View 1 ルート作成 | ST | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/652
EP04-I21-S02 | Sub-issue | Dựng View 3 公開・版履歴 | ST | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/653
EP04-I21-S03 | Sub-issue | Kiểm E2E SCR-07 View 1 / 3 | ST | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/654
EP04-I22 | Issue | Màn SCR-07 View 2 拘束時間チェック | S5 | FE | 7 | 13 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/655
EP04-I22-S01 | Sub-issue | Dựng View 2 E-1〜E-8 | S5 | FE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/656
EP04-I22-S02 | Sub-issue | Kiểm E2E View 2 | S5 | QA | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/657
EP04-I23 | Issue | Lịch trình tài xế SCR-08 View 1 (版 mới nhất, 2 chuyến / ngày, cache) | S4 | BE | 10 | 18.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/658
EP04-I23-S01 | Sub-issue | Cài API schedule / seen | S4 | BE | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/659
EP04-I23-S02 | Sub-issue | Dựng View 1 当日スケジュール | S4 | FE | 4 | 7.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/660
EP04-I23-S03 | Sub-issue | Kiểm quyền và offline View 1 | S4 | QA | 3 | 5.5 | firm | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/661
EP-06 | Epic | トレーサビリティ・回収 — truy vết lô và recall |  |  | 135 | 250 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/662
EP06-I01 | Issue | Dựng màn SCR-11 トレーサビリティ検索 | S6 | FE | 13 | 24 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/663
EP06-I01-S01 | Sub-issue | Viết DD SCR-11 | S5 | SA | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/664
EP06-I01-S02 | Sub-issue | Viết test case SCR-11 | S6 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/665
EP06-I01-S03 | Sub-issue | Code FE màn SCR-11 | S6 | FE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/666
EP06-I02 | Issue | Xây API truy vết thượng / hạ nguồn theo lô, 仕入先ロット, SKU, nhà cung cấp | S6 | BE | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/667
EP06-I03 | Issue | Xây lane 牛: tìm theo 牛個体識別番号 và trả đủ giao dịch | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/668
EP06-I04 | Issue | Xây lane 米: hiển thị đủ trường truy xuất BR-TRACE-01 | S6 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/669
EP06-I05 | Issue | Xây lane 社内ロット và hai loại 終端 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/670
EP06-I06 | Issue | Đạt truy vết lô 3 năm ≤ 60 giây | S6 | BE | 10 | 18.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/671
EP06-I07 | Issue | Hiển thị bản ghi truy vết migrate (legacy_trace_record) | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/672
EP06-I08 | Issue | Dựng màn SCR-12 phần recall (View 1 danh sách ca, View 2 ca recall) | S6 | FE | 13 | 24 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/673
EP06-I08-S01 | Sub-issue | Viết DD SCR-12 phần recall | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/674
EP06-I08-S02 | Sub-issue | Viết test case SCR-12 phần recall | S6 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/675
EP06-I08-S03 | Sub-issue | Code FE View 1–2 SCR-12 | S6 | FE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/676
EP06-I09 | Issue | Mở ca recall và chốt phạm vi (scoped) với 範囲版 1 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/677
EP06-I09-S01 | Sub-issue | Viết DD luồng chốt phạm vi recall (F-TRC-02) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/678
EP06-I10 | Issue | Tự 隔離 lô trong phạm vi và giải phóng 引当 khi scoped | S6 | BE | 10 | 18.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/679
EP06-I11 | Issue | Đổi phạm vi recall thành 範囲版 n+1 và bắt buộc 取消通知 | S6 | BE | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/680
EP06-I12 | Issue | Xây bảng đối chiếu hai đẳng thức và đóng ca recall | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/681
EP06-I12-S01 | Sub-issue | Viết DD luồng đối chiếu và đóng ca (F-TRC-05) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/682
EP06-I13 | Issue | Xây thông báo recall có phiên bản, duyệt hai người và gửi qua IF-MAIL-01 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/683
EP06-I13-S01 | Sub-issue | Viết DD luồng thông báo recall (F-TRC-03) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/684
EP06-I14 | Issue | Xây tác vụ ca recall và cột 担当 / 期限 | S6 | BE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/685
EP06-I15 | Issue | Xây 取消 và 再開 ca recall | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/686
EP06-I15-S01 | Sub-issue | Viết DD luồng 取消 / 再開 (F-TRC-06) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/687
EP06-I16 | Issue | Xây 保全依頼 từ ca recall theo người gửi (X-8 (a)) | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/688
EP06-I16-S01 | Sub-issue | Viết DD luồng 保全依頼 (F-TRC-07) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/689
EP06-I17 | Issue | Xuất RPT-21 リコール追跡票 (PDF) | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/690
EP06-I18 | Issue | Xuất RPT-20 POD・クレーム票 (PDF) | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/691
EP06-I19 | Issue | Kiểm thiết bị PC và MFA cho thao tác duyệt recall ở server | S6 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/692
EP06-I20 | Issue | Kiểm thử luồng truy vết / recall theo ACC-TRC-01 | S6 | QA | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/693
EP-07 | Epic | 報告・KPI — 12 báo cáo vận hành và audit export |  |  | 135 | 250 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/694
EP07-I01 | Issue | Dựng màn SCR-13 運用レポート/KPI | S6 | FE | 12 | 22 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/695
EP07-I01-S01 | Sub-issue | Viết DD SCR-13 | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/696
EP07-I01-S02 | Sub-issue | Viết test case SCR-13 | S6 | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/697
EP07-I01-S03 | Sub-issue | Code FE màn SCR-13 | S6 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/698
EP07-I02 | Issue | Xây danh mục báo cáo, 閲覧ロール và 基準日時 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/699
EP07-I03 | Issue | Xây xuất CSV chung có manifest và nhật ký | S6 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/700
EP07-I04 | Issue | Xây batch B-06 kpi_daily và job dọn export dở | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/701
EP07-I04-S01 | Sub-issue | Viết DD batch B-06 (F-RPT-04) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/702
EP07-I05 | Issue | Xây RPT-02 期限接近 theo hạn giao hợp đồng | S6 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/703
EP07-I06 | Issue | Xây RPT-10 ドライバー遵守 có cột 事象起因 tách riêng | S6 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/704
EP07-I07 | Issue | Xây RPT-04 HACCP欠落 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/705
EP07-I08 | Issue | Xây RPT-05 温度逸脱 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/706
EP07-I09 | Issue | Xây RPT-06 アラームSLA (review trong 15 phút) | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/707
EP07-I10 | Issue | Xây RPT-01 期限別在庫 tách 賞味 / 消費 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/708
EP07-I11 | Issue | Xây RPT-03 隔離 và RPT-07 受入差異 | S6 | BE | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/709
EP07-I12 | Issue | Xây RPT-08 配送実績 và RPT-09 POD完全性 | S6 | BE | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/710
EP07-I13 | Issue | Xây RPT-11 リコール照合 | S6 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/711
EP07-I14 | Issue | Xây RPT-12 監査変更履歴 (chỉ xem) | S6 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/712
EP07-I15 | Issue | Dựng màn SCR-15 監査ログ検索 | S6 | FE | 11 | 20.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/713
EP07-I15-S01 | Sub-issue | Viết DD SCR-15 | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/714
EP07-I15-S02 | Sub-issue | Viết test case SCR-15 | S6 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/715
EP07-I15-S03 | Sub-issue | Code FE màn SCR-15 | S6 | FE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/716
EP07-I16 | Issue | Xây API tìm và xem nhật ký kiểm toán chỉ đọc | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/717
EP07-I17 | Issue | Xây tạo gói RPT-13 監査エクスポート có manifest SHA-256 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/718
EP07-I17-S01 | Sub-issue | Viết DD luồng RPT-13 (F-RPT-02) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/719
EP07-I18 | Issue | Xây 再作成して照合 cho gói RPT-13 | S6 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/720
EP07-I19 | Issue | Xây 依頼 Legal hold / アーカイブ từ SCR-15 | S6 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/721
EP07-I19-S01 | Sub-issue | Viết DD luồng 依頼 từ SCR-15 (F-RPT-05) | S5 | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/722
EP07-I20 | Issue | Chạy nền cho CSV lớn và gói RPT-13 | S6 | BE | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/723
EP07-I21 | Issue | Kiểm thử báo cáo và audit export | S6 | QA | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/724
EP-11 | Epic | 法令再検証 — xác minh lại nguồn pháp lý (OPS-LAW-01) |  |  | 31 | 57.5 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/725
EP11-I01 | Issue | Xác minh lại giá trị 改善基準告示 cho ルール版 giờ lái | P10 | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/726
EP11-I02 | Issue | Chốt 36協定 và ngoại lệ giờ lái áp cho tài xế Yuki | P10 | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/727
EP11-I03 | Issue | Kiểm lại phạm vi 米トレサ法 / 牛トレサ法 áp cho Yuki | P10 | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/728
EP11-I04 | Issue | Xác định mức HACCP Yuki áp dụng và 手引書 tham chiếu | P10 | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/729
EP11-I05 | Issue | Xác minh định nghĩa 賞味期限 / 消費期限 theo quy định ghi nhãn | P10 | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/730
EP11-I06 | Issue | Xác nhận 1/3・1/2 là tập quán hợp đồng, không phải luật | P10 | BrSE | 1 | 2 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/731
EP11-I07 | Issue | Xác minh thời hạn lưu hồ sơ và nghĩa vụ dữ liệu (L-1…L-6) | P10 | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/732
EP11-I08 | Issue | Đóng gói bằng chứng pháp lý cho DR đóng băng thiết kế | P10 | PM | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/733
EP11-I09 | Issue | Kiểm lại nguồn pháp lý trước go / no-go | UAT | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/734
EP-12 | Epic | データ移行 — migration 6 nguồn có lineage và đối soát |  |  | 106 | 196.5 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/735
EP12-I01 | Issue | Thiết kế chi tiết migration: job B-13, lineage, mapping 6 nguồn | S3 | SA | 10 | 18.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/736
EP12-I01-S01 | Sub-issue | Viết DD job B-13 và lineage | S3 | SA | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/737
EP12-I01-S02 | Sub-issue | Viết DD mapping 6 nguồn ①〜⑥ | S3 | SA | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/738
EP12-I02 | Issue | Xây khung job migration có lineage một dòng / dòng thô | S4 | BE | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/739
EP12-I03 | Issue | Profile dữ liệu nguồn và chạy workshop mapping với データオーナー | S4 | BrSE | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/740
EP12-I04 | Issue | Xây loader MIG.1 master (SKU / 顧客 / 仕入先) | S4 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/741
EP12-I05 | Issue | Xây loader MIG.2 lô và tồn theo zone | S5 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/742
EP12-I06 | Issue | Chuẩn hóa lịch sử xuất 3 năm (ngày nhiều định dạng, hạn trống, dòng âm) | S5 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/743
EP12-I07 | Issue | Nạp lịch sử xuất làm mốc 日付逆転 và ánh xạ mã khách đổi | S5 | BE | 10 | 18.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/744
EP12-I08 | Issue | Xây loader MIG.4 dữ liệu nhiệt độ ~2,5 triệu bản ghi | S5 | BE | 9 | 16.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/745
EP12-I09 | Issue | Xây loader MIG.7 tệp 米原産地 và 牛個体識別番号 | S5 | BE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/746
EP12-I10 | Issue | Xây loader MIG.5 chỉ mục route / POD | S6 | BE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/747
EP12-I11 | Issue | Xuất RPT-15 移行照合レポート từ lineage | S5 | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/748
EP12-I12 | Issue | Chạy dry run migration trên môi trường test | S6 | BE | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/749
EP12-I13 | Issue | Chạy rehearsal 1 và đối soát | S6 | BE | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/750
EP12-I14 | Issue | Lấy chữ ký danh sách ngoại lệ sau rehearsal 1 và sửa dữ liệu | HARD | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/751
EP12-I15 | Issue | Chạy rehearsal 2 và quyết định nạp lần cuối | UAT | BE | 10 | 18.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/752
EP-13 | Epic | カットオーバー・UAT・教育・ハイパーケア |  |  | 90 | 167 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/753
EP13-I01 | Issue | Lập kế hoạch UAT 6 tuần theo kịch bản R-06 | ST | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/754
EP13-I02 | Issue | Chuẩn bị môi trường UAT, tài khoản theo 職務 và dữ liệu mask | ST | Infra | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/755
EP13-I03 | Issue | Hỗ trợ UAT đợt 1 (04-05 → 04-16) | UAT | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/756
EP13-I04 | Issue | Hỗ trợ UAT đợt 2 (04-19 → 04-30) cùng rehearsal 2 | UAT | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/757
EP13-I05 | Issue | Hỗ trợ UAT đợt 3 (05-03 → 05-14) và biên bản G5 nghiệp vụ | UAT | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/758
EP13-I06 | Issue | Dựng khung đào tạo: sandbox mask, bài kiểm tra, hồ sơ đào tạo | UAT | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/759
EP13-I07 | Issue | Soạn tài liệu đào tạo nhóm 倉庫 và 品質 | UAT | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/760
EP13-I08 | Issue | Soạn tài liệu đào tạo nhóm 配車 và ドライバー | UAT | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/761
EP13-I09 | Issue | Soạn tài liệu đào tạo nhóm CS / クレーム, 管理者 / サポート, 監査 | UAT | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/762
EP13-I10 | Issue | Tổ chức đào tạo 7 nhóm và kiểm tra (05-17 → 05-21) | CUT | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/763
EP13-I11 | Issue | Viết runbook cutover và hàng đợi đơn thủ công khi đóng băng đơn | UAT | SA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/764
EP13-I12 | Issue | Diễn tập rollback trên UAT | UAT | Infra | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/765
EP13-I13 | Issue | Đóng băng master T-5 ngày (05-27) | CUT | PM | 2 | 3.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/766
EP13-I14 | Issue | Đóng băng đơn T-8 giờ, trích xuất cuối, nạp lần cuối và đối soát | CUT | BE | 15 | 28 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/767
EP13-I15 | Issue | Smoke test E2E sau nạp với 6 owner | CUT | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/768
EP13-I16 | Issue | Họp go / no-go và lấy chữ ký 6 owner (ACC-GO-01) | CUT | PM | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/769
EP13-I17 | Issue | Giám sát chạy song song 1 tuần (hệ cũ chỉ đọc) | HYP | BrSE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/770
EP13-I18 | Issue | Hypercare tuần 1–2: trực sự cố và báo cáo SLA | HYP | BE | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/771
EP13-I19 | Issue | Hypercare tuần 3–4 và bàn giao vận hành (PLAN-B7) | HYP | PM | 4 | 7.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/772
EP-14 | Epic | QA自動化 — bộ R-06, E2E và hồi quy |  |  | 60 | 111 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/773
EP14-I01 | Issue | Dựng khung test tự động E2E / API trong CI | S3 | QA | 5 | 9.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/774
EP14-I02 | Issue | Nạp fixture R-06 vào bộ test | S3 | QA | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/775
EP14-I03 | Issue | Tự động hóa ca 温度boundary | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/776
EP14-I04 | Issue | Tự động hóa ca hai loại hạn (賞味 / 消費) | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/777
EP14-I05 | Issue | Tự động hóa ca 日付逆転 (date reversal) | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/778
EP14-I06 | Issue | Tự động hóa ca route infeasible (giờ lái 2024) | S6 | QA | 5 | 9.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/779
EP14-I07 | Issue | Tự động hóa ca rice / beef (trường truy xuất có kiểu và tìm kiếm) | S6 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/780
EP14-I08 | Issue | Tự động hóa ca POD term (車上渡し / 軒先渡し) | S5 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/781
EP14-I09 | Issue | Tự động hóa ca dirty migration | S6 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/782
EP14-I10 | Issue | Tự động hóa ca FEFO nhiều lô cùng SKU | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/783
EP14-I11 | Issue | Tự động hóa ca cửa sổ giao theo 顧客-SKU | S4 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/784
EP14-I12 | Issue | Tự động hóa ca 牛個体識別番号 sai định dạng | S6 | QA | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/785
EP14-I13 | Issue | Tự động hóa E2E luồng kho ACC-FUN-01 | HARD | QA | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/786
EP14-I14 | Issue | Chạy hồi quy toàn bộ ở Hardening / ST và lập TR | HARD | QA | 8 | 15 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/787
EP14-I15 | Issue | Chạy hồi quy cho mỗi bản sửa trong UAT | UAT | QA | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/788
EP-15 | Epic | Quản lý dự án / BrSE |  |  | 64 | 118.5 |  |  | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/789
EP15-I01 | Issue | Dựng khung quản trị: báo cáo tuần, RAID, decision log, CR board | P10 | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/790
EP15-I02 | Issue | Báo cáo tuần và RAID giai đoạn 1.0 – S0 | P10 | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/791
EP15-I03 | Issue | Báo cáo tuần và RAID S1–S2 | S5 | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/792
EP15-I04 | Issue | Báo cáo tuần và RAID S3–S4 (bắt đầu 移行) | ST | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/793
EP15-I05 | Issue | Báo cáo tuần và RAID S5–S6 (rehearsal 1) | S6 | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/794
EP15-I06 | Issue | Báo cáo tuần và RAID Hardening – ST (G4, G5 kỹ thuật) | ST | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/795
EP15-I07 | Issue | Báo cáo tuần và RAID giai đoạn UAT (G5 nghiệp vụ) | UAT | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/796
EP15-I08 | Issue | Báo cáo hằng ngày khi cutover và báo cáo hypercare | HYP | PM | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/797
EP15-I09 | Issue | Gửi và theo dõi lô Q&A 69 câu, chốt CR lab4 | P10 | BrSE | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/798
EP15-I10 | Issue | Theo dõi câu hỏi chặn trước S4 (dữ liệu 移行, layout IF, pháp lý) | HARD | BrSE | 3 | 5.5 | placeholder | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/799
EP15-I11 | Issue | Q&A với khách và dịch phản hồi trong UAT | UAT | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/800
EP15-I12 | Issue | Re-estimate bottom-up bằng SWP và so với bidding | P10 | PM | 6 | 11 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/801
EP15-I13 | Issue | Cập nhật PREMISE và baseline sau re-estimate và Q&A | P10 | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/802
EP15-I14 | Issue | Cập nhật PREMISE, RTM và ma trận tuân thủ trước G4 | HARD | BrSE | 4 | 7.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/803
EP15-I15 | Issue | Tổ chức demo cách tuần và review với khách S1–S3 | S3 | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/804
EP15-I16 | Issue | Tổ chức demo cách tuần và review với khách S4–S6 | S6 | BrSE | 3 | 5.5 | provisional | Todo | https://github.com/linhvtm-2475/yuki-wms-backlog/issues/805

## Giờ theo sprint × epic
Sprint | Bắt đầu | Số ngày | EP-00 | EP-10 | EP-08 | EP-09 | EP-01 | EP-02 | EP-05 | EP-03 | EP-04 | EP-06 | EP-07 | EP-11 | EP-12 | EP-13 | EP-14 | EP-15 | Tổng
P10 | 2026-10-26 | 33 | [11 empty] | 52 |  |  |  | 42 | 94
S0 | 2026-11-30 | 7 | 148 | 20 | 16 | 13 | [12 empty] | 197
S1 | 2026-12-07 | 14 | 294 | 16 | 92 | 38 | 32 |  |  | 6 | 28 | [7 empty] | 506
S2 | 2026-12-21 | 21 | 26 | 16 | 80 | 50 | 190 | 41 |  | 72 | 63 | [7 empty] | 538
S3 | 2027-01-11 | 14 |  |  | 28 | 26 |  | 76 | 24 | 274 | 50 |  |  |  | 19 |  | 15 | 6 | 518
S4 | 2027-01-25 | 14 |  | 11 | 56 | 11 |  | 40 | 178 | 122 | 52 |  |  |  | 38 |  | 22 |  | 530
S5 | 2027-02-08 | 21 | 46 | 90 | 46 |  |  |  | 116 |  | 134 | 66 | 48 |  | 72 |  | 11 | 8 | 637
S6 | 2027-03-01 | 14 | 26 | 45 |  |  |  |  | 22 |  |  | 187 | 205 |  | 44 |  | 26 | 13 | 568
HARD | 2027-03-15 | 7 |  | 130 | 6 |  |  | 8 | [6 empty] | 6 |  | 30 | 13 | 193
ST | 2027-03-22 | 14 |  | 30 | 36 | 102 | 48 | 40 |  | 92 | 48 |  |  |  |  | 17 |  | 15 | 428
UAT | 2027-04-05 | 42 | [11 empty] | 6 | 18 | 73 | 8 | 15 | 120
CUT | 2027-05-17 | 15 | [13 empty] | 52 |  |  | 52
HYP | 2027-06-01 | 28 | [13 empty] | 26 |  | 8 | 34